## PROCUREMENT PLAN
PROCUREMENT PLAN FOR KING FAISAL HOSPITAL - RWANDA FOR FISCAL YEAR 2022-2023 | KFH PROCUREMENT PLAN 2022-2023
No | Title of Tender | Type of tender (Works, Goods or Services) | Estimated Budget in Rwf | Proc Methods | Source of Funds | Date for Receipt of TOR/Specifications and advertisement | Date for reception of Proposals/BIDS | Tender Opening Date | Date of evaluation By HTB | Notification | Contract signing Date | Contract completion Date
1 | Renovation of existing maternity | Works | 363700000 | NCB | Govt | 25/9/2023 | 16/10/2023 | 16/10/2023 | 21/10/2023 | 2023-12-11 | 19/11/2023 | 18/4/2024
2 | Rehabilitation of ICU and HDU | Works | 204516936 | NCB | Govt | 25/9/2023 | 16/10/2023 | 16/10/2023 | 21/10/2023 | 2023-12-11 | 19/11/2023 | 18/4/2024
3 | Guest house refurbishment | Works | 240000000 | NCB | Govt | 25/9/2023 | 16/10/2023 | 16/10/2023 | 21/10/2023 | 2023-12-11 | 19/11/2023 | 18/4/2024
4 | Completion of remaining works for Block VI | Works | 350000000 | NCB | Govt | 2022-09-10 | 30/10/2023 | 30/10/2023 | 2023-05-11 | 26/11/2023 | 2023-02-12 | 2024-01-04
5 | Execution of works for NICU expansion | Works | 150000000 | CB | Govt | 2022-09-10 | 30/10/2023 | 30/10/2023 | 2023-05-11 | 26/11/2023 | 2023-02-12 | 2024-01-04
6 | Overhauling of air handling unit for operating theaters and ICU | Works | 400000000 | NCB | Govt | 2022-09-10 | 30/10/2023 | 30/10/2023 | 2023-05-11 | 26/11/2023 | 2023-02-12 | 2024-01-04
7 | Rehabilitation of the sewage treatment plan | Works | 70000000 | NCB | Govt | 2022-09-10 | 30/10/2023 | 30/10/2023 | 2023-05-11 | 26/11/2023 | 2023-02-12 | 2024-01-04
8 | Upgrade of the solar energy at the OPD Roof top | Works | 80000000 | NCB | Govt | 2022-09-10 | 30/10/2023 | 30/10/2023 | 2023-05-11 | 26/11/2023 | 2023-02-12 | 2024-01-03
9 | Supervision of works | Consultancy service | 50000000 | NCB/QCBS | Govt | 20/9/2023 | 2023-04-10 | 2023-04-10 | 2023-09-10 | 30/10/2023 | 21/11/2023 | 18/5/2024
10 | Supply and installation of Equipment and furniture for the reformed Administration Block into Neurology and Chemotherapy units | Goods | 120771669 | ICB | Govt | 25/08/2023 | 25/09/2023 | 25/09/2023 | 30/9/2023 | 21/10/2023 | 2023-10-11 | 2024-10-03
11 | Supply and installation Equipment and furniture for the expanded and renovated of Accident and Emergency unit | Goods | 207339253.6 | ICB | Govt | 25/08/2023 | 25/09/2023 | 25/09/2023 | 30/9/2023 | 21/10/2023 | 2023-10-11 | 2024-10-03
12 | Supply and installation of Equipment and furniture for the rehabilitated Old OPD in KFH main buidling into Gastro-enterology (Endoscopy) unit | Goods | 321358712 | ICB | Govt | 25/08/2023 | 25/09/2023 | 25/09/2023 | 30/9/2023 | 21/10/2023 | 2023-10-11 | 2024-10-03
13 | Supply and installation of equipment and furniture for the new mortuary building to be constructed in 2023 | Goods | 439332190 | ICB | Govt | 25/08/2023 | 25/09/2023 | 25/09/2023 | 30/9/2023 | 21/10/2023 | 2023-10-11 | 2024-10-03
14 | Supply and installation of medical and non medical equipment for Ketamine and Ophthalmology Clinics to be built in 2023 | Goods | 165635825 | ICB | Govt | 20/07/2023 | 20/08/2023 | 20/08/2023 | 25/08/2023 | 16/09/2023 | 25/09/2023 | 25/12/2023
15 | Supply and installation of Other medical equipment approved in the Sustainability Plan | Goods | 3366313009 | ICB | Govt | 20/9/2023 | 20/10/2023 | 20/10/2023 | 25/10/2023 | 16/11/2023 | 30/11/2023 | 30/04/2024
16 | Supply of spare parts for the maintenance of electrical, plumbing, mechanical, civil works, paintings and Acs for KFH | Goods | 354082000 | NCB | KFHR | 20/08/2023 | 2023-11-09 | 2023-11-09 | 15/9/2023 | 2023-06-10 | 14/10/2023 | 13/10/2024
17 | Supply and installation of lifts to replace the olders ones | Goods | 300000000 | NCB | KFHR | 20/08/2023 | 2023-11-09 | 2023-11-09 | 15/9/2023 | 2023-06-10 | 14/10/2023 | 13/10/2024
18 | Supply and installation of laundry machines | Goods | 140000000 | NCB | Govt | 20/08/2023 | 2023-11-09 | 2023-11-09 | 15/9/2023 | 2023-06-10 | 14/10/2023 | 13/10/2024
19 | Supply of FUEL | Goods | 90000000 | NCB | KFHR | 2023-10-11 | 25/11/2023 | 25/11/2023 | 30/11/2023 | 21/12/2023 | 2023-05-01 | 2024-04-01
20 | Supply of PAPER TOWEL | Goods | 80000000 | NCB | KFHR | 2023-10-09 | 25/10/2023 | 25/10/2023 | 30/10/2023 | 21/11/2023 | 2023-05-12 | 2024-04-12
21 | Supply of Linen, work wears(Uniforms) and PPEs(Shoes, face masks, gloves protection glasses,…) | Goods | 141000000 | ICB | KFHR | 20/08/2023 | 20/9/2023 | 20/9/2023 | 25/09/2023 | 16/11/2023 | 2023-05-12 | 2024-04-12
22 | Supply of dry foods, fresh foods, meat, water and milk for KFH Kitchen | Goods | 750000000 | NCB | KFHR | 20/07/2023 | 20/08/2023 | 20/08/2023 | 25/08/2023 | 16/09/2023 | 25/09/2023 | 25/12/2023
23 | Supply of laundry detergents and consumables | Goods | 29646640 | NCB | KFHR | 30/9/2023 | 15/10/2023 | 15/10/2023 | 20/10/2023 | 2023-11-11 | 25/11/2023 | 24/11/2024
24 | Annual maintenance for the picture for the archiving and communication sytem(PACS) | Non consultancy service | 30000000 | SSS | KFHR | NA | NA | NA | 2024-01-01 | NA | 23/1/2024 | 23/01/2025
25 | Provision of services for the maintenance of MRI and Cathlab | Non consultancy service | 300000000 | SSS | KFHR | NA | NA | NA | NA | NA | NA | NA
26 | Provision of internet services | Non consultancy service | 50000000 | SSS | KFHR | NA | NA | NA | NA | NA | NA | NA
27 | Maintenance of UPS | Service | 30000000 | SSS | KFHR | NA | NA | NA | 2024-10-03 | NA | 15/03/2024 | 14/03/2025
28 | Maintenance of call center | Service | 30000000 | SSS | KFHR | NA | NA | NA | 30/4/2024 | NA | 2024-02-05 | 2025-02-05
29 | Maintenance of KFH lifts | Non consultancy service | 40000000 | NCB | KFHR | 25/06/2024 | 16/7/2024 | 16/7/2024 | 21/07/2024 | 2024-12-08 | 20/8/2024 | 20/08/2025
30 | Provision of legal Services | Consultancy service | 25000000 | NCB | KFHR | 20/02/2024 | 2024-06-03 | 2024-06-03 | 11/03/20224 | 2024-03-04 | 2024-10-04 | 2025-09-04
31 | Provision of garages services | Non consultancy service | 60000000 | NCB | KFHR | 2024-10-04 | 25/04/2024 | 25/04/2024 | 30/04/2024 | 21/05/2024 | 30/06/2024 | 29/06/2025
32 | Provision of communication and promotional materials under annual framework contract | Service | 50000000 | NCB | KFHR | 2024-10-05 | 25/05/2024 | 25/05/2024 | 30/5/2024 | 21/05/2024 | 30/06/2024 | 29/06/2025
33 | Provision of catering services | Service | 746300000 | NCB | KFHR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/10/2024
34 | Provision of clearance services | Service | 50000000 | NCB | KFHR | 15/12/2023 | 29/12/2023 | 29/12/2023 | 2024-03-01 | 24/1/2024 | 2024-05-02 | 2025-04-02
35 | Maintenance of IT equipment under annual framework contract | Non consultancy service | 100000000 | NCB | KFHR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/10/2024
36 | Printing and supply of medical of forms for KFH under annual framework contract | Goods | 300000000 | NCB | KFHR | 30/03/2023 | 16/04/2023 | 16/04/2023 | 21/04/2023 | 21/05/2023 | 2023-07-06 | 2024-06-06
37 | Supply of drugs and Consumables for KFH | Goods | 6492261604 | OCB | KFHR | 2023-05-07 | 2023-08-08 | 2023-08-08 | 15/8/2023 | 15/9/2023 | 30/9/2023 | 29/9/2024
38 | Consultancy service to update the KFHR Procurement manual and standard bidding documents | Goods | 20000000 | Individual Consultancy | KFHR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/12/2023
39 | Provision of cleaning services for KFH Premises | Services | 222000000 | NCB | KFHR | 15/9/2023 | 30/9/2023 | 30/9/2023 | 2023-05-10 | 30/10/2023 | 15/11/2023 | 14/11/2024
40 | Provision of medical waste disposal | Goods | 87300000 | NCB | KFHFR | 15/4/2024 | 30/4/2024 | 30/4/2024 | 2024-05-05 | 30/5/2024 | 15/6/2024 | 14/6/2025
41 | Provision of fumigation services | Services | 8136000 | NCB | KHFR | 15/7/2023 | 2023-05-08 | 2023-05-08 | 2023-10-08 | 25/8/2023 | 30/8/2023 | 30/8/2024
42 | Supply and installation of IT equipment | Goods | 324300000 | NCB | KFHR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/10/2024
43 | Maintenance of various IT equipment(CCTV cameras and IT equipment) | Services | 60000000 | NCB | KHFR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/10/2024
44 | Supply and installation of Hospital cabling and network upgrade | Goods | 140000000 | NCB | KHFR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/1/2024
45 | Laboratory Reagents | Goods | 765673108 | NCB | KHFR | 2024-10-06 | 25/6/2024 | 25/6/2024 | 30/6/2024 | 21/7/2024 | 30/7/2024 | 29/7/2025
46 | Global Insurance | Service | 120000000 | Restricted | KHFR | 2024-10-06 | 25/6/2024 | 25/6/2024 | 30/6/2024 | 21/7/2024 | 30/7/2024 | 29/7/2025
47 | Staff medical insurance | Service | 775680000 | Restricted | KHFR | 2024-10-06 | 25/6/2024 | 25/6/2024 | 30/6/2024 | 21/7/2024 | 30/7/2024 | 29/7/2025
48 | Security equipment | Goods | 116500000 | NCB | KFHR | 2023-10-09 | 25/10/2023 | 25/10/2023 | 30/10/2023 | 21/11/2023 | 2023-05-12 | 2024-04-12
49 | Provision of security services | Sevices | 80000000 | NCB | KHFR | 15/4/2024 | 30/4/2024 | 30/4/2024 | 2024-05-05 | 30/5/2024 | 15/6/2024 | 14/6/2025
50 | Fire fighting equipment maintenance | Service | 13000000 | NCB | KHFR | 15/7/2023 | 2023-05-08 | 2023-05-08 | 2023-10-08 | 25/8/2023 | 30/8/2023 | 30/8/2024
51 | Biomedical Spare parts | Goods | 697723000 | NCB | KHFR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/1/2024
52 | Office furniture materials for various Hospital Offices | Goods | 116933665 | NCB | KFHR | 2023-10-09 | 25/10/2023 | 25/10/2023 | 30/10/2023 | 21/11/2023 | 2023-05-12 | 2024-05-02
53 | Provision of vehicle insurance | Service | 8008363 | Restricted | KFHR | 15/4/2024 | 30/4/2024 | 30/4/2024 | 2024-05-05 | 30/5/2024 | 15/6/2024 | 14/6/2025

## PP WORKS CAPEX
Title of Tender | Type of tender (Works, Goods or Services) | Estimated Budget in Rwf | Procurement Methods | Source of Funds | Date for Receipt of TOR/Specifications and advertisement | Date for reception of Proposals/BIDS | Tender Opening Date | Date of evaluation By HTB | Notification | Contract signing Date | Contract completion Date
Renovation of existing maternity | Works | 363700000 | NCB | Govt | 25/9/2023 | 16/10/2023 | 16/10/2023 | 21/10/2023 | 2023-12-11 | 19/11/2023 | 18/4/2024
Rehabilitation of ICU and HDU | Works | 204516936 | NCB |  | 25/9/2023 | 16/10/2023 | 16/10/2023 | 21/10/2023 | 2023-12-11 | 19/11/2023 | 18/4/2024
Guest house refurbishment | Works | 240000000 | NCB |  | 25/9/2023 | 16/10/2023 | 16/10/2023 | 21/10/2023 | 2023-12-11 | 19/11/2023 | 18/4/2024
Completion of remaining works for Block VI | Works | 350000000 | NCB | Govt | 2022-09-10 | 30/10/2023 | 30/10/2023 | 2023-05-11 | 26/11/2023 | 2023-02-12 | 2024-01-04
Execution of works for NICU expansion | Works | 150000000 | CB |  | 2022-09-10 | 30/10/2023 | 30/10/2023 | 2023-05-11 | 26/11/2023 | 2023-02-12 | 2024-01-04
Overhauling of air handling unit for operating theaters and ICU | Works | 400000000 | NCB | Govt | 2022-09-10 | 30/10/2023 | 30/10/2023 | 2023-05-11 | 26/11/2023 | 2023-02-12 | 2024-01-04
Rehabilitation of the sewage treatment plan | Works | 70000000 | NCB |  | 2022-09-10 | 30/10/2023 | 30/10/2023 | 2023-05-11 | 26/11/2023 | 2023-02-12 | 2024-01-04
Upgrade of the solar energy at the OPD Roof top | Works | 80000000 | NCB |  | 2022-09-10 | 30/10/2023 | 30/10/2023 | 2023-05-11 | 26/11/2023 | 2023-02-12 | 2024-01-03
Supervision of works | Consultancy service | 50000000 | NCB/QCBS | Govt | 20/9/2023 | 2023-04-10 | 2023-04-10 | 2023-09-10 | 30/10/2023 | 21/11/2023 | 18/5/2024
1908216936

## PP CAPEX EQUIPMENT
PROCUREMENT PLAN : MEDICAL AND NON EQUIPMENT
No | Title of Tender | Type of tender (Works, Goods or Services) | Estimated Budget in Rwf | Procurement Methods | Source of Funds | Date for Receipt of TOR/Specifications and advertisement | Date for reception of Proposals/BIDS | Tender Opening Date | Date of evaluation By HTB | Notification | Contract signing Date | Contract completion Date
1 | Supply and installation of Equipment and furniture for the reformed Administration Block into Neurology and Chemotherapy units | Goods | 120771669 | ICB | Govt | 25/08/2023 | 25/09/2023 | 25/09/2023 | 30/9/2023 | 21/10/2023 | 2023-10-11 | 2024-10-03
2 | Supply and installation Equipment and furniture for the expanded and renovated of Accident and Emergency unit | Goods | 207339253.6 | ICB | Govt | 25/08/2023 | 25/09/2023 | 25/09/2023 | 30/9/2023 | 21/10/2023 | 2023-10-11 | 2024-10-03
3 | Supply and installation of Equipment and furniture for the rehabilitated Old OPD in KFH main buidling into Gastro-enterology (Endoscopy) unit | Goods | 321358712 | ICB | Govt | 25/08/2023 | 25/09/2023 | 25/09/2023 | 30/9/2023 | 21/10/2023 | 2023-10-11 | 2024-10-03
4 | Supply and installation of equipment and furniture for the new mortuary building to be constructed in 2023 | Goods | 439332190 | ICB | Govt | 25/08/2023 | 25/09/2023 | 25/09/2023 | 30/9/2023 | 21/10/2023 | 2023-10-11 | 2024-10-03
5 | Supply and installation of medical and non medical equipment for Ketamine and Ophthalmology Clinics to be built in 2023 | Goods | 165635825 | ICB | Govt | 20/07/2023 | 20/08/2023 | 20/08/2023 | 25/08/2023 | 16/09/2023 | 25/09/2023 | 25/12/2023
6 | Supply and installation of Other medical equipment approved in the Sustainability Plan | Goods | 3366313009 | ICB | Govt | 20/9/2023 | 20/10/2023 | 20/10/2023 | 25/10/2023 | 16/11/2023 | 30/11/2023 | 30/04/2024
4620750658.6

## PP OPEX OTHERS
No | Title of Tender | Type of tender (Works, Goods or Services) | Estimated Budget in Rwf | Procurement Methods | Source of Funds | Date for Receipt of TOR/Specifications and advertisement | Date for reception of Proposals/BIDS | Tender Opening Date | Date of evaluation By HTB | Notification | Contract signing Date | Contract completion Date
1 | Supply of spare parts for the maintenance of electrical, plumbing, mechanical, civil works, paintings and Acs for KFH | Goods | 354082000 | NCB | KFHR | 20/08/2023 | 2023-11-09 | 2023-11-09 | 15/9/2023 | 2023-06-10 | 14/10/2023 | 13/10/2024
2 | Supply and installation of lifts to replace the olders ones | Goods | 300000000 | NCB | KFHR | 20/08/2023 | 2023-11-09 | 2023-11-09 | 15/9/2023 | 2023-06-10 | 14/10/2023 | 13/10/2024
3 | Supply and installation of laundry machines | Goods | 140000000 | NCB | Govt | 20/08/2023 | 2023-11-09 | 2023-11-09 | 15/9/2023 | 2023-06-10 | 14/10/2023 | 13/10/2024
4 | Supply of FUEL | Goods | 90000000 | NCB | KFHR | 2023-10-11 | 25/11/2023 | 25/11/2023 | 30/11/2023 | 21/12/2023 | 2023-05-01 | 2024-04-01
5 | Supply of PAPER TOWEL | Goods | 80000000 | NCB | KFHR | 2023-10-09 | 25/10/2023 | 25/10/2023 | 30/10/2023 | 21/11/2023 | 2023-05-12 | 2024-04-12
7 | Supply of Linen, work wears(Uniforms) and PPEs(Shoes, face masks, gloves protection glasses,…) | Goods | 141000000 | ICB | KFHR | 20/08/2023 | 20/9/2023 | 20/9/2023 | 25/09/2023 | 16/11/2023 | 2023-05-12 | 2024-04-12
8 | Supply of dry foods, fresh foods, meat, water and milk for KFH Kitchen | Goods | 750000000 | NCB | KFHR | 20/07/2023 | 20/08/2023 | 20/08/2023 | 25/08/2023 | 16/09/2023 | 25/09/2023 | 25/12/2023
9 | Supply of laundry detergents and consumables | Goods | 29646640 | NCB | KFHR | 30/9/2023 | 15/10/2023 | 15/10/2023 | 20/10/2023 | 2023-11-11 | 25/11/2023 | 24/11/2024
10 | Annual maintenance for the picture for the archiving and communication sytem(PACS) | Non consultancy service | 30000000 | SSS | KFHR | NA | NA | NA | 2024-01-01 | NA | 23/1/2024 | 23/01/2025
11 | Provision of services for the maintenance of MRI and Cathlab | Non consultancy service | 300000000 | SSS | KFHR | NA | NA | NA | NA | NA | NA | NA
12 | Provision of internet services | Non consultancy service | 50000000 | SSS | KFHR | NA | NA | NA | NA | NA | NA | NA
13 | Maintenance of UPS | Service | 30000000 | SSS | KFHR | NA | NA | NA | 2024-10-03 | NA | 15/03/2024 | 14/03/2025
14 | Maintenance of call center | Service | 30000000 | SSS | KFHR | NA | NA | NA | 30/4/2024 | NA | 2024-02-05 | 2025-02-05
15 | Maintenance of KFH lifts | Non consultancy service | 40000000 | NCB | KFHR | 25/06/2024 | 16/7/2024 | 16/7/2024 | 21/07/2024 | 2024-12-08 | 20/8/2024 | 20/08/2025
16 | Provision of legal Services | Consultancy service | 25000000 | NCB | KFHR | 20/02/2024 | 2024-06-03 | 2024-06-03 | 11/03/20224 | 2024-03-04 | 2024-10-04 | 2025-09-04
17 | Provision of garages services | Non consultancy service | 60000000 | NCB | KFHR | 2024-10-04 | 25/04/2024 | 25/04/2024 | 30/04/2024 | 21/05/2024 | 30/06/2024 | 29/06/2025
18 | Provision of communication and promotional materials under annual framework contract | Service | 50000000 | NCB | KFHR | 2024-10-05 | 25/05/2024 | 25/05/2024 | 30/5/2024 | 21/05/2024 | 30/06/2024 | 29/06/2025
19 | Provision of catering services | Service | 746300000 | NCB | KFHR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/10/2024
20 | Provision of clearance services | Service | 50000000 | NCB | KFHR | 15/12/2023 | 29/12/2023 | 29/12/2023 | 2024-03-01 | 24/1/2024 | 2024-05-02 | 2025-04-02
21 | Maintenance of IT equipment under annual framework contract | Non consultancy service | 100000000 | NCB | KFHR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/10/2024
22 | Printing and supply of medical of forms for KFH under annual framework contract | Goods | 300000000 | NCB | KFHR | 30/03/2023 | 16/04/2023 | 16/04/2023 | 21/04/2023 | 21/05/2023 | 2023-07-06 | 2024-06-06
23 | Supply of drugs and Consumables for KFH | Goods | 6492261604 | OCB | KFHR | 2023-05-07 | 2023-08-08 | 2023-08-08 | 15/8/2023 | 15/9/2023 | 30/9/2023 | 29/9/2024
24 | Consultancy service to update the KFHR Procurement manual and standard bidding documents | Goods | 20000000 | Individual Consultancy | KFHR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/12/2023
25 | Provision of cleaning services for KFH Premises | Services | 222000000 | NCB | KFHR | 15/9/2023 | 30/9/2023 | 30/9/2023 | 2023-05-10 | 30/10/2023 | 15/11/2023 | 14/11/2024
26 | Provision of medical waste disposal | Goods | 87300000 | NCB | KFHFR | 15/4/2024 | 30/4/2024 | 30/4/2024 | 2024-05-05 | 30/5/2024 | 15/6/2024 | 14/6/2025
27 | Provision of fumigation services | Services | 8136000 | NCB | KHFR | 15/7/2023 | 2023-05-08 | 2023-05-08 | 2023-10-08 | 25/8/2023 | 30/8/2023 | 30/8/2024
28 | Supply and installation of IT equipment | Goods | 324300000 | NCB | KFHR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/10/2024
29 | Maintenance of various IT equipment(CCTV cameras and IT equipment) | Services | 60000000 | NCB | KHFR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/10/2024
30 | Supply and installation of Hospital cabling and network upgrade | Goods | 140000000 | NCB | KHFR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/1/2024
31 | Laboratory Reagents | Goods | 765673108 | NCB | KHFR | 2024-10-06 | 25/6/2024 | 25/6/2024 | 30/6/2024 | 21/7/2024 | 30/7/2024 | 29/7/2025
32 | Global Insurance | Service | 120000000 | Restricted | KHFR | 2024-10-06 | 25/6/2024 | 25/6/2024 | 30/6/2024 | 21/7/2024 | 30/7/2024 | 29/7/2025
33 | Staff medical insurance | Service | 7756800000 | Restricted | KHFR | 2024-10-06 | 25/6/2024 | 25/6/2024 | 30/6/2024 | 21/7/2024 | 30/7/2024 | 29/7/2025
34 | Security equipment | Goods | 116500000 | NCB | KFHR | 2023-10-09 | 25/10/2023 | 25/10/2023 | 30/10/2023 | 21/11/2023 | 2023-05-12 | 2024-04-12
35 | Provision of security services | Sevices | 80000000 | NCB | KHFR | 15/4/2024 | 30/4/2024 | 30/4/2024 | 2024-05-05 | 30/5/2024 | 15/6/2024 | 14/6/2025
36 | Fire fighting equipment maintenance | Service | 13000000 | NCB | KHFR | 15/7/2023 | 2023-05-08 | 2023-05-08 | 2023-10-08 | 25/8/2023 | 30/8/2023 | 30/8/2024
37 | Biomedical Spare parts | Goods | 697723000 | NCB | KHFR | 30/8/2023 | 15/9/2023 | 15/9/2023 | 20/09/2023 | 15/10/2023 | 30/10/2023 | 30/1/2024
38 | Office furniture materials for various Hospital Offices | Goods | 116933665 | NCB | KFHR | 2023-10-09 | 25/10/2023 | 25/10/2023 | 30/10/2023 | 21/11/2023 | 2023-05-12 | 2024-05-02
39 | Provision of vehicle insurance | Service | 8008363 | Restricted | KFHR | 15/4/2024 | 30/4/2024 | 30/4/2024 | 2024-05-05 | 30/5/2024 | 15/6/2024 | 14/6/2025
20724664380

## reports
PROCUREMENT PLAN FOR KING FAISAL HOSPITAL - RWANDA FOR FISCAL YEAR 2022-2023
No | Title of Tender | Type of tender (Works, Goods or Services) | Estimated Budget in Rwf | Date of signature | Date of contract closure | Contract Amount | status
1 | Consultancy Services for a Salary and Benefits Survey and Job Evaluation | Consultancy service | 40000000 | 2022-07-11 | 60days | 16400700 | Contract executed
2 | Consultancy Services for conducting WISN study for KFH - Rwanda staff | Consultancy service | 30000000 | 2022-11-24 | 60days | 29325000 | ongoing contract up to 23th March 2023 as the contract was extended for additional 60 days
3 | Provision of legal Services | Consultancy service | 25000000 | 30 12 2022 | 30 12 2023 | 14520000 | ongoing contract
4 | Performance of various laboratory tests | Consultancy service | 50000000 | 2022-11-08 | 2023-11-07 | Unit prices | ongoing contract
5 | Consultancy services for the recruitment of an Architect for providing BOQs and drawings for the reformation for various Hospital buildings | Consultancy service | 10000000 | 07 11 2022 | 31 03 2023 | 9004500 | ongoing contract
6 | Consultancy service for the revision of KFH Procurement manual, procurement policies and providing standard bidding documents for KFH | Consultancy service | 15000000 | Not yet | Not yet | Not yet | Waiting ministerial order
7 | Consultancy service for the recruitment of an independent Surveyor to review the quantities used for the construction of KFH OPD | Consultancy service | 15000000 | 2022-12-22 | 30 days | 13500000 | Under contract execution(draft report of items identification, specifcations and Quantification is available)
8 | Supply , installation and commissioning of medical equipment for Ear, Nose, Throat | Goods | 89749489 | Not yet | Not yet | Not yet | under publication process
9 | Supply, installation and commissioning of medical equipment for ICU | Goods | 100000000 | Not yet | Not yet | Not yet | under publication process
10 | Supply, installation and commissioning of cardiothoracic equipment | Goods | 80000000 | Not yet | Not yet | Not yet | under publication process
11 | Supply, installation and commissioning of operating theatre and laboratory equipment for KFH | Goods | 150000000 | Not yet | Not yet | Not yet | under publication process
12 | Supply of stationary | Goods | 80000000 | 2023-01-13 | 2023-01-12 | Unit prices | ongoing contract
13 | Supply of FUEL | Goods | 90000000 | 2023-12-02 | 2023-12-02 | 2023-12-02 | ongoing contract
14 | Supply of PAPER TOWEL | Goods | 80000000 | 26 09 2022 | 26 09 2023 | Based on unit Cost | ongoing contract
15 | Supply of labaratory reagents and consumables | Goods | 200000000 | 2022-01-03 | 2023-04-03 | 2022-09-25 | preparation of Tender document
16 | Supply of dry foods, fruits, vegetables and meat for KFH Kitchen | Goods | 450000000 | 2023-01-13 | 2024-01-12 | Unit prices | ongoing contract
17 | Installation of electrical solar energy power system for King faisal Hospital Rwanda | Goods | 0 | Not yet | Not yet |  | Under Evaluation
18 | Supply, installation and commissioning of IT equipment under annual framework contract | Goods | 150000000 | Not yet | Not yet |  | Preparation of Tender document
19 | Supply of attires for clinical and non clinical KFH staff under annual framework contract | Goods | 200000000 | Not yet | Not yet |  | Preparation of Tender document
20 | Printing and supply of medical of forms for KFH under annual framework contract | Goods | 300000000 | Not yet | Not yet |  | Preparation of Tender document
21 | Supply of drugs and Consumables for KFH | Goods | 2000000000 | 2022-03-12 | 2023-03-11 | unit prices | Ongoing contract/Review of medical requirements for publication
22 | Consultancy service for accounting manual development, updating the existing financial policies and developing new ones to comply with applicable laws and regulations | Goods | 20000000 | Not yet | Not yet |  | under publication
23 | Supply, installation and commissioning of maternity equipment for KFH | Goods | 1000000000 | 15 01 2023 | 15 04 2023 | 911546734 | Under contract execution
24 | Moving Mortuary | Non consultancy service | 67695000 | Not yet | Not yet |  | Under evaluation process
25 | Annual maintenance for the picture for the archiving and communication sytem(PACS) | Non consultancy service | 30000000 | 2022-01-24 | 2023-01-23 |  | ongoing contract
26 | Provision of services for the maintenance of MRI and Cathlab | Non consultancy service | 300000000 | 30.09.2022 | 29.09.2027 | 209242129 | ongoing contract
27 | Provision of internet services | Non consultancy service | 50000000 | 2022-10-05 | 2024-10-02 | Unit prices | ongoing contract
28 | Maintenance of KFH lifts | Non consultancy service | 40000000 | 28 01 2023 | 27 01 2024 | 12,458 USD | ongoing contract
29 | Provision of garages services | Non consultancy service | 60000000 | 22 12 2022 | 21 04 2023 | Based on unit prices | ongoing contract
30 | Maintenance of IT equipment under annual framework contract | Non consultancy service | 100000000 | Not yet | Not yet |  | Preparation of Tender document
31 | Call for Expression of Interest (EOI) to Enhancing the Hospital Management Information System (HMIS) | Service | 1000000000 | Not yet | Not yet | 1,300,000 USD | under contract signature
32 | Provision of communication and promotional materials under annual framework contract | Service | 20000000 | Not yet | Not yet |  | Preparation of Tender document
33 | Provision of maintenance services for electrical, mechanical, plumbing ,… under annual framework contract | Service | 60000000 | Not yet | Not yet |  | under notification
34 | Provision of Health insurance for KFH Rwanda staff | Service | 100000000 | 2022-08-31 | 2023-08-30 | 605676300 | Ongoing contract
35 | Recruitment of a sport coach for KFH staff physical fitness | Service | 10000000 | Not yet | Not yet |  | Preparation of Tender document
36 | Provision of clearance services | Service | 50000000 | Not yet | Not yet |  | under notifications
37 | Consultancy service for the supervision of the construction works for the construction of various works | Service/QCBS | 100000000 | Not yet | Not yet |  | under evaluation process
38 | Provision of cleaning services for KFH Premises | Services | 200000000 | 20 12 2022 | 21 12 2023 | 6,123,770Rwf/Month | Ongoing contract
39 | Execution of works for the construction of King Faisal Hospital Fence | Works | 427000000 | Not yet | Not yet |  | Under evaluation process
40 | Execution of works for Accident and Emergency Expansion with an operating room | Works | 357260000 | Govt | Not yet |  | Under evaluation process
41 | Execution of works for Repurposing of Consultation rooms to IP Rooms & Endoscopy | Works | 213284521 | Not yet | Not yet |  | Under evaluation process
42 | Execution of works for Maternity Ward Renovation with an operating room for C-section | Works | 363700000 | 2022-01-06 | 15 02 2023 | 3911685790 | Ongoing contract
43 | Execution of works for the Rehabilitation of water tank | Works | 75125937 | Not yet | Not yet |  | Under evaluation process
44 | Construction of Ketamine and Ophtamology block at King Faisal Hospital | Works | 450000000 | Not yet | Not yet |  | Under publications