## Initial Proc Plan
No | Tender Type | Tender Title | Tender Method | Allocated Budget | Source of funds | Planned tender document preparation date | Planned Publication date | Planned Bid opening date | Planned Provisional Notification date | Planned Contract signing date | Planned Contract Management start date | Planned Contract closure date
1 | Works | Execution of works for Renovation of existing maternity and NICU expansion | NCB | 580265485 | Govt | 23/09/2024 | 2024-09-26 | 2024-10-18 | 2024-11-08 | 2024-11-25 | 2024-11-25 | 2025-05-25
2 |  | Execution of works for construction of permeable paved parking and access roads at King Faisal Hospital Rwanda | NCB | 310000000 | KFHR | 13/08/2024 | 2024-08-15 | 2024-08-29 | 2024-09-18 | 2024-09-30 | 2024-09-30 | 2024-11-30
3 |  | Execution of works for construction of mammography room | SRT | 27652120 | KFHR | 2024-07-25 | 31/07/2024 | 06/08/2024 | 2024-08-08 | 22/08/2024 | 22/08/2024 | 22/09/2024
4 |  | Execution of works for completion of ophtalmoligy civil works | NCB | 69550373 | KFHR | 15/11/2024 | 18/11/2024 | 2024-11-12 | 2025-04-01 | 20/01/2025 | 27/01/2025 | 26/05/2025
5 |  | Execution of works for renovation of Accident and Emergency wards | NCB | 580265485 | Govt | 2024-11-01 | 4/011/2024 | 26/11/2024 | 16/12/2024 | 31/12/2024 | 2025-07-01 | 2025-06-06
6 |  | Execution of works for completion of block VI | NCB | 600000000 | Govt | 2024-10-05 | 2024-10-10 | 31/10/2024 | 25/11/2024 | 13/12/2024 | 20/12/2024 | 19/5/2025
7 |  | Supply, installation, testing & commissioning services for the repair and upgrading of the main building sewage treatment plant sewage treatment plant. | NCB | 200000000 | Govt | 25/08/2024 | 30/08/2024 | 21/09/2024 | 14/10/2024 | 29/10/2024 | 2024-03-11 | 2025-03-01
8 | Goods | Supply of electricity (cashpower of Kigali Executive Apartments) under annual framework contract | NCB | 30000000 | KFHR | 30/06/2024 | 2024-02-07 | 25/07/2024 | 20/08/2024 | 30/08/2024 | 2024-01-09 | 30/08/2025
9 |  | Supply of drugs and consumables for cardiac surgeries | NCB | 800000000 | Govt | 2024-12-15 | 2024-12-16 | 2025-01-05 | 2025-01-26 | 2025-02-11 | 2025-02-11 | 2025-06-11
10 |  | Supply and installation of ophtalmolohy equipment at King Faisal Hospital , RWANDA | NCB | 430321578 | Govt | 25/08/2024 | 30/08/2024 | 21/09/2024 | 15/10/2024 | 30/10/2024 | 2024-05-11 | 2025-05-02
11 |  | Supply and installation of Oxygen plant | NCB | 400000000 | Govt | 2024-09-10 | 13/10/2024 | 2024-05-11 | 28/11/2024 | 13/12/2024 | 2024-11-11 | 2025-10-03
12 |  | Supply and installation of different spare parts for maintenance of Oxygen plant , Generator, Sewage system and autoclaves under framework contract. | NCB | 41033000 | KFHR | 2024-09-10 | 13/10/2024 | 2024-05-11 | 28/11/2024 | 14/12/2024 | 19/12/2024 | 18/12/2025
13 |  | Supply of maintenance accessories and tools for Biomedical equipment under framework contract | NCB | 61523000 | KFHR | 2024-10-11 | 15/11/2024 | 2024-07-12 | 30/12/2024 | 15/01/2025 | 15/01/2025 | 14/01/2026
14 |  | Supply of laundry machines spare parts under framework contract | NCB | 23875500 | KFHR | 2024-10-11 | 15/11/2024 | 2024-07-12 | 30/12/2024 | 15/01/2025 | 15/01/2025 | 14/01/2026
15 |  | Supply and installation of air conditioning and refrigerants spare parts under framework contract | NCB | 22300000 | KFHR | 2024-10-11 | 15/11/2024 | 2024-07-12 | 30/12/2024 | 15/01/2025 | 15/01/2025 | 14/01/2026
16 |  | Supply of tool kits and consummables for Plumbing, electricity, masonry capentry and welding under framework contract | NCB | 226469680 | KFHR | 2024-10-11 | 15/11/2024 | 2024-07-12 | 30/12/2024 | 15/01/2025 | 15/01/2025 | 14/01/2026
17 |  | Supply of vehicle 's tires for 11 different vehicles under framework contract | NCB | 15509600 | KFHR | 2024-10-11 | 14/11/2024 | 2024-06-12 | 28/12/2024 | 13/01/2025 | 13/01/2025 | 2026-12-01
18 |  | Supply of office stationery | NCB | 210529100 | KFHR | 2025-05-03 | 2025-10-03 | 31/03/2025 | 22/04/2025 | 2025-10-05 | 2025-10-05 | 2026-10-05
19 |  | Supply of assorted items | NCB | 54000000 | KFHR | 15/03/2025 | 20/03/2025 | 15/04/2025 | 2025-08-05 | 23/05/2025 | 23/05/2025 | 23/05/2026
20 |  | Supply and installation of Nurse Call System | NCB | 250000000 | KFHR | 2024-12-12 | 15/12/2024 | 2025-10-01 | 31/01/2025 | 15/02/2025 | 15/02/2025 | 15/06/2025
21 |  | Supply of FUEL and GAZ to King Faisal Hospital Rwanda. | NCB | 220271295 | KFHR | 2024-12-15 | 2024-12-16 | 2025-01-05 | 2025-01-26 | 2025-02-11 | 2025-02-11 | 2026-02-11
22 |  | Supply of Linen, work wears(Uniforms) | NCB | 280000000 | KFHR | NA | NA | NA | NA | NA | 2024-01-08 | 2025-01-08
23 |  | Supply of dry foods products | NCB | 214873196 | KFHR | NA | NA | NA | NA | NA | 2024-01-13 | 2025-01-14
24 |  | Supply of fresh foods products | NCB | 283465116 | KFHR | NA | NA | NA | NA | NA | 2024-06-14 | 2025-06-14
25 |  | Supply of meat | NCB | 48977996 | KFHR | NA | NA | NA | NA | NA | 2024-01-13 | 2025-01-13
26 |  | Supply of beverages (water, milk , juices ,…) | NCB | 94041996 | KFHR | NA | NA | NA | NA | NA | 28/5/2024 | 28/5/2025
27 |  | Supply of cleaning products and laundry detergents | NCB | 29646640 | KFHR | 2024-08-05 | 13/05/2024 | 2024-03-06 | 25/06/2024 | 2024-05-06 | 2024-05-06 | 2025-05-06
28 |  | printing and supply of medical forms for KFHR under framework contract | NCB | 87209000 | KFHR | 2024-11-25 | 2024-11-26 | 2024-12-17 | 2025-01-07 | 2025-01-20 | 2025-01-20 | 2025-04-20
29 |  | Supply of drugs and Consumables( for OPD, inpatients, Implants, dental, Radiology, Kidney Transplants) | NCB | 5492261604 | KFHR | NA | NA | NA | NA | NA | 2024-02-20 | 2025-02-19
30 |  | Supply and installation of ICT equipment( Computers,printers,scaners,photocopiers,and others IT accessories) under framework contract | NCB | 104900000 | KFHR | 2024-11-28 | 2024-11-30 | 2024-12-21 | 2025-01-07 | 2025-01-22 | 2025-01-22 | 2025-04-21
31 |  | Supply of laboratory Reagents | NCB | 765673108 | KFHR | NA | NA | NA | NA | NA | 2023-11-15 | 2023-11-15
32 |  | Supply and installation of security equipment ( Walkthrough metal detector , Cameras , luggages scanners, road blocks etc,...) and tools, | NCB | 198250000 | KFHR | 2024-12-02 | 2024-12-05 | 2024-12-27 | 2025-01-13 | 2025-01-28 | 2025-01-28 | 2025-04-27
33 |  | Supply of hardware for civil mechanical , electrical and plumbing maintenance for Kacyiru Executive Apartment (KEA) | NCB | 60000000 | KFHR | NA | NA | NA | NA | NA | 2024-01-02 | 2025-01-02
34 |  | Supply and installation of office furniture under framework contract | NCB | 116933665 | KFHR | 2023-05-12 | NA | NA | NA | NA | 30/02/2024 | 29/02/2025
35 |  | Design, supply, installation, maintenance of Procurement system and provision of training to users at KFHR | NCB | 100000000 | KFHR | 2024-11-05 | 2024-11-10 | 2024-12-01 | 2024-12-22 | 2025-01-07 | 2025-01-10 | 2026-01-09
36 | Non Consultancy services | Provision of customs clearance services | NCB | 7800000 | KFHR | NA | NA | NA | NA | NA | NA | 2025-08-05
37 |  | Provision of communication and promotional materials under annual framework contract | NCB | 45657000 | KFHR | NA | NA | NA | NA | NA | NA | 27/10/2024
38 |  | Provision of cleaning services for KFH Premises | NCB | 73485240 | KFHR | NA | NA | NA | NA | NA | NA | 2024-12-20
39 |  | Provision of emptying tank services under framework contract | NCB | 6960000 | KFHR | 2024-06-27 | 2024-07-02 | 2024-07-25 | 2024-08-15 | 2024-08-23 | 2024-08-23 | 2025-08-23
40 |  | Provision of services for the maintenance of MRI and Cathlab | ss | 258000000 | KFHR | NA | NA | NA | NA | NA | NA | 30/09/2024
41 |  | Provison services for routine maintenance for laboratory services under frameworks contract | NCB | 50000000 | KFHR | 2024-10-10 | 2024-10-13 | 2024-11-04 | 2024-12-25 | 2025-01-10 | 2025-01-10 | 2026-01-10
42 |  | Provision service for vehicles management (GPS) under framework contract | NRT | 6000000 | KFHR | 2024-10-10 | 2024-10-13 | 2024-11-04 | 2024-12-25 | 2025-01-10 | 2025-01-10 | 2026-01-10
43 |  | Provision of internet services | ss | 63720000 | KFHR | NA | NA | NA | NA | NA | NA | 2024-10-05
44 |  | Maintenance of UPS | ss | 30000000 | KFHR | NA | NA | NA | NA | NA | NA | 14/03/2025
45 |  | Maintenance of call center | ss | 30000000 | KFHR | NA | NA | NA | NA | NA | NA | 2025-02-05
46 |  | Maintenance of KFH lifts | SS | 40000000 | KFHR | NA | NA | NA | NA | NA | NA | 27/11/2024
47 |  | Provision of vehicles maintenance ( garage services for 11 vehicles) | NCB | 89156200 | KFHR | 2024-06-27 | 2024-07-02 | 2024-07-25 | 2024-08-15 | 2024-08-23 | 2024-08-23 | 2025-08-23
48 |  | Provision services for networking cabling revamping mainly for main building | NCB | 140000000 | KFHR | 2024-10-27 | 2024-10-30 | 2024-11-21 | 2024-12-07 | 2024-12-15 | 2024-12-15 | 2025-04-15
49 |  | Provision of services for upgrade of the solar energy at the OPD Roof top | NRT | 20000000 | KFHR | 2024-09-25 | 2024-10-30 | 2024-11-21 | 2024-12-07 | 2024-12-15 | 2024-12-15 | 2025-02-15
50 |  | Provision of medical waste disposal | SS | 87300000 | KFHR | NA | NA | NA | NA | NA | NA | 2025-06-30
51 |  | Provision of fumigation services | NCB | 10800000 | KFHR | NA | NA | NA | NA | NA | 2023-01-03 | 03/011/2024
52 |  | Provision services for maintenance of various IT equipment | NCB | 100000000 | KFHR | 26/010/2024 | 2024-10-30 | 2024-11-21 | 2024-12-07 | 2024-12-15 | 2024-12-15 | 154/12/2025
53 |  | Provision of services for Maintenance of CCTV Cameras | NCB | 24500000 | KFHR | NA | NA | NA | NA | NA | 2024-08-25 | 2025-08-25
54 |  | Global Insurance | NRT | 120000000 | KFHR | NA | NA | NA | NA | NA | NA | 2025-08-01
55 |  | Staff medical insurance | NRT | 950000000 | KFHR | NA | NA | NA | NA | NA | NA | 2025-08-01
56 |  | Performance of various laboratory test | SS | 30000000 | KFHR | NA | NA | NA | NA | NA | NA | 2023-09-11
57 |  | Provisin of service for cleaning of RSSB Tower II and KACYIRU Executive Apartment (KEA) | NCB | 70000000 | KFHR | NA | NA | NA | NA | NA | 2024-01-02 | 2025-01-02
58 |  | Provision of services for maintenance of sewage treatment plant for RSS Properties | NCB | 3540000 | KFHR | NA | NA | NA | NA | NA | 2024-01-02 | 2025-01-02
59 |  | Provision of services for maintenance of of items for RSSB buldings (lift ) Kacyiru Executive Apartment (KEA) | NCB | 11667840 | KFHR | NA | NA | NA | NA | NA | 2024-01-02 | 2025-01-02
60 |  | Provision of services for maintenance of of items for RSSB buldings (Cameras ) Kacyiru Executive Apartment (KEA) | NCB | 1628400 | KFHR | NA | NA | NA | NA | NA | 2024-01-02 | 2025-01-02
61 |  | Provision of services for maintenance of Fire fighting equipment | NCB | 40000000 | KFHR | NA | NA | NA | NA | NA | 2023-12-22 | 2024-12-22
62 |  | Provision of security services | ss | 11648000 | KFHR | NA | NA | NA | NA | NA | NA | 2025-01-03
63 |  | Provision of vehicle insurance | NCB | 18502211 | KFHR | NA | NA | NA | NA | NA | NA | 2025-05-20
64 | Consultancy Services | Supervision of various works | NCB | 150000000 | Govt | 23/09/2024 | 2024-09-26 | 2024-10-18 | 2024-11-08 | 2024-11-25 | 2024-11-25 | 2025-06-25
65 |  | Provision of legal Services | NCB | 25000000 | KFHR | NA | NA | NA | NA | NA | NA | 25/02/2025
66 |  | Provision of hospital information System and Maintenance (SISOFT) | SSS | 565,000,000, | KFHR | NA | NA | NA | NA | NA | NA | 22/4/2029
15517511308
ABEBE ZERIHUN, KFHR Chief Executive Officer Prof. JACOB SOUOPGUI, KFHR Board of Directors Chairman
Client Centered care
KING FAISAL HOSPITAL, RWANDA
OFFICE OF THE DEPUTY CHIEF EXECUTIVE OFFICER
Note on C12: Richard: This is not clear, will discuss tomorrow

## To be removed
PROCUREMENT PLAN 2024-2025: REMOVED TENDERS
No | Tender Title | Tender Method | Reason for removal
1 | Execution of works for Renovation of existing maternity and NICU expansion | NCB | No budget
2 | Execution of works for completion of ophtalmoligy civil works | NCB | No budget
3 | Execution of works for renovation of Accident and Emergency wards | NCB | No budget, to be done by Foundation
4 | Execution of works for completion of block VI | NCB | No budget, to be done by Foundation
5 | Supply and installation of Oxygen plant | NCB | No budget
6 | Supply and installation of different spare parts for maintenance of Oxygen plant , Generator, Sewage system and autoclaves under framework contract. | NCB | No budget
7 | Supply of maintenance accessories and tools for Biomedical equipment under framework contract | NCB | No budget
8 | Supply of laundry machines spare parts under framework contract | NCB | No budget
9 | Supply and installation of air conditioning and refrigerants spare parts under framework contract | NCB | No budget
10 | Supply of vehicle 's tires for 11 different vehicles under framework contract | NCB | Done of RFQ Basis
11 | Provision of services for routine maintenance for laboratory services under frameworks contract | NCB | No budget
12 | Provision service for vehicles management (GPS) under framework contract | NRT | No budget
13 | Provision services for networking cabling revamping mainly for main building | NCB | No budget
14 | Provision services for maintenance of various IT equipment | NCB | Will be carried out by IT Technicians
OF

## to be added
PROCUREMENT PLAN 2024-2025: ADDED TENDERS
No | Tender Title | Tender Method
1 | Supply of air compressor and vaccumo pump at King Faisal Hospital Rwanda | NCB
2 | Supply and installation of warehouse storage solution material handling finished goods storage at King Faisal Hospital Rwanda. | NCB
3 | Supply and installation of OPD Pharmacy counters and shelves for medical display at KFHR | Restricted
4 | Supply and installation of electrical,IT ,CCTV and HVAC at KFHR | Restricted
5 | Consultancy services for review and cleaning up of past financial data at King Faisal Hospital Rwanda. | NCB/QCBS
6 | Supply and installation of generator for main hospital building at King Faisal Hospital Rwanda. | NCB
7 | Provision of maintenance services for the OPD Sewage treatment plant at King Faisal Hospital Rwanda | NCB
8 | Execution of works for the extension of OPD Pharmacy at KFHR | NCB
9 | Execution of works for the construction of administration, education, training and research building for KFHR | ICB
10 | Provision of maitenance services for the repair of furniture at KFHR under framework contract | NCB
11 | Supply and installaton of pediatric equipment for KFHR | NCB
12 | Supply and installation of Radiology equipment for KFHR | SS(RMS)
Note on B9: Richard: This is not clear, will discuss tomorrow

## Revised proc plan
KFHR REVISED PROCUREMENT PLAN 2024-2025
No | Tender Type | Tender Title | Tender Method | Source of funds | Planned tender document preparation date | Planned Publication date | Planned Bid opening date | Planned Provisional Notification date | Planned Contract signing date | Planned Contract Management start date | Planned Contract closure date
1 | Works | Execution of works for construction of permeable paved parking and access roads at King Faisal Hospital Rwanda | NCB | KFHR | 13/08/2024 | 2024-08-15 | 2024-08-29 | 2024-09-18 | 2024-09-30 | 2024-09-30 | 2024-11-30
2 |  | Execution of works for construction of mammography room | SRT | KFHR | 2024-07-25 | 31/07/2024 | 06/08/2024 | 2024-08-08 | 22/08/2024 | 22/08/2024 | 22/09/2024
3 |  | Execution of works for the extension of OPD Pharmacy at KFHR | SRT | KFHR | 2025-02-04 | 07/02/2025 | 14/02/2025 | 2025-03-10 | 17/03/2025 | 20/03/2025 | 19/05/2025
4 |  | Execution of works for the construction of administration, education, training and research building for KFHR | ICB | SDF&KFHR | 2025-02-05 | 10/02/2025 | 15/04/2025 | 2025-05-06 | 30/05/2025 | 30/05/2025 | 30/05/2026
5 |  | Execution of works for repair upgrading of the main sewage treatment plant and related civil works at KFHR | NCB | Govt | 25/08/2024 | 30/08/2024 | 21/09/2024 | 14/10/2024 | 29/10/2024 | 2024-03-11 | 2025-03-01
6 | Goods | Supply of electricity (cashpower of Kigali Executive Apartments) under annual framework contract | NCB | KFHR | 30/06/2024 | 2024-02-07 | 25/07/2024 | 20/08/2024 | 30/08/2024 | 2024-01-09 | 30/08/2025
7 |  | Supply of drugs and consumables for cardiac surgeries | NCB | Govt | 2024-12-15 | 2024-12-16 | 2025-01-05 | 2025-01-26 | 2025-02-11 | 2025-02-11 | 2025-06-11
8 |  | Supply and installation of ophtalmolohy equipment at King Faisal Hospital , RWANDA | NCB | Govt | 25/08/2024 | 30/08/2024 | 21/09/2024 | 15/10/2024 | 30/10/2024 | 2024-05-11 | 2025-05-02
9 |  | Supply of materials for plumbing,electricity,mechanical ,air condiotioning and refrigeration under framework contract at King Faisal Hospital Rwanda | NCB | KFHR | 15/01/2025 | 17/01/2025 | 2025-04-02 | 25/02/2025 | 2025-05-03 | 2025-07-03 | 2026-06-03
10 |  | Supply of office stationery | NCB | KFHR | 2025-05-03 | 2025-10-03 | 31/03/2025 | 22/04/2025 | 2025-10-05 | 2025-10-05 | 2026-10-05
11 |  | Supply of assorted items under framework contract(Extended) | NCB | KFHR | NA | NA | NA | NA | NA | NA | 23/03/2026
12 |  | Supply and installation of Nurse Call System | NCB | KFHR | 2024-12-12 | 15/12/2024 | 2025-10-01 | 31/01/2025 | 15/02/2025 | 15/02/2025 | 15/06/2025
13 |  | Supply of air compressor and vaccum pump at King Faisal Hospital Rwanda | NCB | KFHR | 2024-10-10 | 2024-10-11 | 2024-11-01 | 2024-11-21 | 2024-12-10 | 2025-01-05 | 2025-02-04
14 |  | Supply and installation of green power generator for main hospital building at King Faisal Hospital Rwanda. | NCB | KFHR | 2025-03-15 | 2025-03-31 | 2025-04-21 | 2025-05-14 | 2025-05-19 | 2025-05-19 | 2025-07-18
15 |  | Supply and installation of warehouse storage solution material handling finished goods storage at King Faisal Hospital Rwanda(Shelves) | NCB | KFHR | 2024-12-15 | 2024-12-18 | 2025-01-08 | 2025-01-23 | 2025-01-30 | 2025-01-30 | 2025-03-30
16 |  | Supply of FUEL and GAZ to King Faisal Hospital Rwanda. | NCB | KFHR | 2025-10-03 | 13/03/2025 | 2025-04-04 | 25/04/2025 | 2025-03-05 | 2025-06-06 | 2026-05-05
17 |  | Supply of Linen, work wears(Uniforms) under framework contract(Extended) | NCB | KFHR | NA | NA | NA | NA | NA | 2024-01-08 | 2025-01-08
18 |  | Supply of dry foods and meat at King Faisal Hospital Rwanda | NCB | KFHR | 2024-10-05 | 2024-10-10 | 2024-11-01 | 2024-11-16 | 2024-12-15 | 2025-01-02 | 2026-01-02
19 |  | Supply of fresh foods products at King Faisal Hospital Rwanda under framework contract(To be extended) | NCB | KFHR | NA | NA | NA | NA | NA | 2024-06-14 | 2025-06-14
20 |  | Supply of beverages (water, milk , juices ,…) under framework contract(To be extended) | NCB | KFHR | NA | NA | NA | NA | NA | 28/5/2024 | 28/5/2025
21 |  | Supply of cleaning products and laundry detergents | NCB | KFHR | 2024-08-05 | 13/05/2024 | 2024-03-06 | 25/06/2024 | 2024-05-06 | 2024-05-06 | 2025-05-06
22 |  | Printing and supply of medical forms for KFHR under framework contract | NCB | KFHR | 2024-11-25 | 2024-11-26 | 2024-12-17 | 2025-01-07 | 2025-01-20 | 2025-01-20 | 2025-04-20
23 |  | Supply of drugs and Consumables( for OPD, inpatients, Implants, dental, Radiology, Kidney Transplants) | NCB | KFHR | NA | NA | NA | NA | NA | NA | 2025-05-19
24 |  | Supply of laboratory Reagents | NCB | KFHR | NA | NA | NA | NA | NA | NA | 2025-11-15
25 |  | Supply of hardware for civil mechanical , electrical and plumbing maintenance for Kacyiru Executive Apartment (KEA) | NCB | KFHR | NA | NA | NA | NA | NA | NA | 2025-01-05
26 |  | Supply of promotional materials and provision of video coverage services to King Faisal Hospital Rwanda ; under frame work contract | NCB | KFHR | 2024-10-23 | 2024-10-25 | 2024-11-15 | 2024-11-30 | 2024-12-15 | 2025-01-05 | 2026-01-05
27 |  | Supply and installation of office furniture under framework contract | NCB | KFHR | 2023-05-12 | NA | NA | NA | NA | NA | 29/05/2025
28 |  | Supply and installation of OPD Pharmacy counters and shelves for medical siaplay at KFHR | RST | KFHR | 2025-03-04 | 2025-03-07 | 2025-03-14 | 2025-03-29 | 2025-04-08 | 2025-04-15 | 2025-06-15
29 |  | Supply and installation of electrical,IT ,CCTV and HVAC at KFHR | RST | KFHR | 2025-03-04 | 2025-03-07 | 2025-03-14 | 2025-03-29 | 2025-04-08 | 2025-04-15 | 2025-06-15
30 |  | Supply and installation of Radiology equipment | SS(RMS) | KFHR | 2025-10-03 | NA | NA | NA | NA | NA | NA
31 |  | Supply and installation of peridatric equipment at KFHR | NCB | KFHR | 20/02/2025 | 2025-02-25 | 2025-03-18 | 2025-04-10 | 2025-04-18 | 2025-04-25 | 2025-06-25
32 | Non Consultancy Services | Design, supply, installation, maintenance of Procurement system and provision of training to users at KFHR | NCB | KFHR | 2024-11-05 | 2024-11-10 | 2024-12-01 | 2024-12-22 | 2025-01-07 | 2025-01-10 | 2026-01-09
33 |  | Provision of customs clearance services under framework contract(Extended) | NCB | KFHR | NA | NA | NA | NA | NA | NA | 2025-08-05
34 |  | Provision of cleaning services for KFH Premises | SS | KFHR | NA | NA | NA | NA | NA | NA | 2024-12-20
35 |  | Provision of emptying tank services under framework contract | NCB | KFHR | 14/11/2024 | 16/11/2024 | 2024-05-12 | 26/12/2024 | 2025-05-01 | 2025-08-01 | 2026-07-01
36 |  | Provision of services for the maintenance of MRI and Cathlab | ss | KFHR | NA | NA | NA | NA | NA | NA | 30/09/2024
37 |  | Provision of maitenance services for the repair of furniture at KFHR under framework contract | CNB | KFHR | 2025-04-06 | 2025-04-15 | 2025-05-06 | 2025-05-21 | 2025-05-29 | 2025-05-29 | 2026-05-28
38 |  | Provision of maintenance services for the OPD Sewage treatment plant at King Faisal Hopspital Rwanda | CNB | KFHR | 2025-02-04 | 2025-02-06 | 26/02/02025 | 2025-03-19 | 2025-03-26 | 2025-04-01 | 2026-04-01
39 |  | Provision of internet services | SS | KFHR | NA | NA | NA | NA | NA | NA | 2025-10-05
40 |  | Maintenance of UPS | SS | KFHR | NA | NA | NA | NA | NA | NA | 14/03/2026
41 |  | Maintenance of call center | SS | KFHR | NA | NA | NA | NA | NA | NA | 2026-02-05
42 |  | Maintenance of KFH lifts | SS | KFHR | NA | NA | NA | NA | NA | NA | 27/11/2025
43 |  | Provision of vehicles maintenance ( garage services for 11 vehicles) | NCB | KFHR | 2024-06-27 | 2024-07-02 | 2024-07-25 | 2024-08-15 | 2024-08-23 | 2024-08-23 | 2025-08-23
44 |  | Provision of services for upgrade of the solar energy at the OPD Roof top | NRT | KFHR | 2025-10-04 | 13/04/2025 | 2025-04-05 | 25/05/2025 | 2025-04-06 | 2025-10-06 | 2025-10-08
45 |  | Provision of medical waste disposal | SS | KFHR | NA | NA | NA | NA | NA | NA | 2025-06-30
46 |  | Provision of fumigation services | NCB | KFHR | NA | NA | NA | NA | NA | NA | 03/011/2025
47 |  | Provision of services for Maintenance of CCTV Cameras | NCB | KFHR | NA | NA | NA | NA | NA | 2024-08-25 | 2025-08-25
48 |  | Global Insurance | NRT | KFHR | NA | NA | NA | NA | NA | NA | 2025-08-01
49 |  | Staff medical insurance | NRT | KFHR | NA | NA | NA | NA | NA | NA | 2025-08-01
50 |  | Performance of various laboratory test | SS | KFHR | NA | NA | NA | NA | NA | NA | 2025-09-11
51 |  | Provision of service for cleaning of RSSB Tower II and KACYIRU Executive Apartment (KEA) | NCB | KFHR | NA | NA | NA | NA | NA | NA | 2026-01-02
52 |  | Provision of services for maintenance of sewage treatment plant for RSS Properties | NCB | KFHR | NA | NA | NA | NA | NA | NA | 2026-01-02
53 |  | Provision of services for maintenance of of items for RSSB buldings (lift ) Kacyiru Executive Apartment (KEA) | NCB | KFHR | NA | NA | NA | NA | NA | NA | 2025-01-05
54 |  | Provision of services for maintenance of of items for RSSB buldings (Cameras ) Kacyiru Executive Apartment (KEA) | NCB | KFHR | NA | NA | NA | NA | NA | NA | 2026-01-02
55 |  | Provision of services for maintenance of Fire fighting equipment | NCB | KFHR | NA | NA | NA | NA | NA | NA | 2025-12-22
56 |  | Provision of security services | SS | KFHR | NA | NA | NA | NA | NA | NA | 2026-01-03
57 |  | Provision of vehicle insurance | NCB | KFHR | NA | NA | NA | NA | NA | NA | 2025-05-20
58 |  | Consultancy services for recruitment of a local law firm for the provision of legal services at King Faisal Hospital Rwanda. | NCB | KFHR | NA | NA | NA | NA | NA | NA | 25/02/2025
59 |  | Consultancy services for review and cleaning up of past financial data at King Faisal Hospital Rwanda. | NCB | KFHR | 2024-12-25 | 2025-01-03 | 2025-01-21 | 2025-02-05 | 2025-02-11 | 2025-02-15 | 2025-06-15
60 |  | Provision of hospital information System and Maintenance (SISOFT) | SS | KFHR | NA | NA | NA | NA | NA | NA | 2029-04-22
Client Centered care
KING FAISAL HOSPITAL, RWANDA
OFFICE OF THE DEPUTY CHIEF EXECUTIVE OFFICER
Note on C41: Richard: This is not clear, will discuss tomorrow